**1.0 Initiating**

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *1.1* | *Identify Stakeholders* |
| WBS Element Description | |
| *[3 Hours]* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *1.2* | *Identify communications strategy* |
| WBS Element Description | |
| *[3 Hours]* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *1.3* | *Identify legal standards* |
| WBS Element Description | |
| *[14 Days]* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *1.4* | *Identify accessibility issues* |
| WBS Element Description | |
| *[1 Hour]* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *1.5* | *Identify sporting values* |
| WBS Element Description | |
| *[1 Day]* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *1.6* | *Identify aboriginal culture and values* |
| WBS Element Description | |
| *[21 Days]* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *1.7* | *Prepare project charter* |
| WBS Element Description | |
| *[7 Days]* | |

**2.0 Planning**

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.1* | *Create project assumptions table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.2* | *Prepare project contract* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.3* | *Prepare SWOT analysis of ICT in the AFL* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.3.1* | *Determine strengths, weaknesses, opportunities, threats* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.3.2* | *Craft SWOT analysis table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.3.3* | *Review and finalize SWOT analysis table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.4* | *Prepare Stakeholder analysis table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.4.1* | *Determine internal Stakeholders* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.4.2* | *Determine external Stakeholders* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.4.3* | *Gather Stakeholder data* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.4.3.1* | *Position* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.4.3.2* | *Project role* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.4.3.3* | *Contract information* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.4.4* | *Determine level of interest, importance* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.4.5* | *Craft Stakeholder analysis table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.4.6* | *Review and finalize stakeholder analysis table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.5* | *Plan scope management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.5.1* | *Collect requirements* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.5.1.1* | *Craft preliminary scope table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.5.1.2* | *Craft out of scope table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.5.1.3* | *Craft minimum scope table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.5.2* | *Define scope* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.5.2.1* | *Create project scope statement* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.5.3* | *Create WBS* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.6* | *Prepare schedule and cost baseline* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.6.1* | *Determine task durations* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.6.2* | *Determine task resources* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.6.3* | *Determine task dependencies* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.6.4* | *Create draft Gantt chart* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.6.5* | *Craft cost baseline table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.7* | *Plan risk management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.7.1* | *Identify risks* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.7.2* | *Perform qualitative risk analysis* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.7.3* | *Perform quantitative risk analysis* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.7.4* | *Plan risk response* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.8* | *Plan procurement management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.8.1* | *Determine procurement strategy* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.8.2* | *Craft procurement strategy table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.8.3* | *Craft procurement management table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.9* | *Plan quality management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.9.1* | *Determine quality strategy* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.9.2* | *Craft quality plan table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.10* | *Website planning* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.10.1* | *Identify website purpose* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.10.2* | *Identify website requirements* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.10.3* | *Craft website concept* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.10.4* | *Review and finalize website concept* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.11* | *Application* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.11.1* | *Identify application purpose* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.11.2* | *Identify application requirements* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.11.3* | *Craft application concept* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.11.4* | *Review and finalize application concept* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.12* | *Server* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.12.1* | *Explore business systems* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.12.2* | *Identify optimal business system* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.12.3* | *Identify server management choices* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.12.4* | *Craft server management plan table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *2.12.5* | *Review and finalize server management plan table* |
| WBS Element Description | |
| *WBS Code* | |

**3.0 Executing**

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.1* | *Intranet website content* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.1.1* | *Website templates and tools* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.1.2* | *Website AFL material* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.1.2.1* | *Website article* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.1.2.2* | *Website links* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.1.3* | *Contact players* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.1.4* | *Merchandise* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.1.5* | *Ticketing* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.2* | *Intranet application content* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.2.1* | *Application templates and tools* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.2.2* | *Application AFL material* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.2.2.1* | *Application articles* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.2.2.2* | *Application links* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.2.3* | *Health care information material* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.2.4* | *Accessibility features* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.2.5* | *Social media campaign* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.3* | *Intranet website design* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.4* | *Intranet website construction* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.5* | *Intranet website testing* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.6* | *Intranet website promotion* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.7* | *Intranet website roll-out* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.8* | *Intranet application design* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.9* | *Intranet application construction* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.10* | *Intranet application testing* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.11* | *Intranet application promotion* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.12* | *Intranet application roll-out* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *3.13* | *Project benefits measurement* |
| WBS Element Description | |
| *WBS Code* | |

**4.0 Monitoring and Controlling**

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *4.1* | *Assumption table management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *4.2* | *Quality management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *4.3* | *Risk management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *4.4* | *Scope management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *4.5* | *Procurement management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *4.6* | *Cost baseline management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *4.7* | *Server management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *4.8* | *Time management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *4.9* | *Stakeholder engagement management* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *4.10* | *Progress reports* |
| WBS Element Description | |
| *WBS Code* | |

**5.0 Closing**

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.1* | *Prepare final Gantt chart* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.2* | *Prepare final scope table* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.3* | *Prepare final scope statement* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.4* | *Prepare final project report* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.4.1* | *Collect and review progress reports* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.4.1.1* | *Create progress summary report* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.4.1.2* | *Review and finalize progress summary report* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.4.2* | *Review and finalize final project report* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.4.3* | *Prepare glossary terms* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.5* | *Prepare final project presentation* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.5.1* | *Title page* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.5.2* | *Executive summary* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.5.3* | *Table of contents* |
| WBS Element Description | |
| *WBS Code* | |

|  |  |
| --- | --- |
| WBS Code | WBS Element |
| *5.5.4* | *Report summary* |
| WBS Element Description | |
| *WBS Code* | |