1. **Initiating**
   1. Identifying Stakeholders
   2. Identify communications strategy
   3. Identify legal standards
   4. Identify accessibility issues
   5. Identify sporting values
   6. Identify aboriginal culture and values
   7. Prepare project charter
2. **Planning**
   1. Create project assumptions table
   2. Prepare project contract
   3. Prepare SWOT analysis of ICT in the AFL
      1. Determine strengths, weaknesses, opportunities, threats
      2. Craft SWOT analysis table
      3. Review and finalize SWOT analysis table
   4. Prepare Stakeholder analysis table
      1. Determine internal Stakeholders
      2. Determine external Stakeholders
      3. Gather Stakeholder data
         1. Position
         2. Project role
         3. Contact information
      4. Determine level of interest, importance
      5. Craft Stakeholder analysis table
      6. Review and finalize Stakeholder analysis table
   5. Plan scope management
      1. Collect requirements
         1. Craft preliminary scope table
         2. Craft out of scope table
         3. Craft minimum scope table
         4. Review and finalize scope tables
      2. Define scope
         1. Create project scope statement
         2. Review and finalize scope tables
      3. Create WBS
   6. Prepare schedule and cost baseline
      1. Determine task durations
      2. Determine task resources
      3. Determine task dependencies
      4. Create draft Gantt chart
      5. Review and finalize Gantt chart
      6. Craft cost baseline table
      7. Review and finalize cost baseline table
   7. Plan risk management
      1. Identify risks
      2. Perform qualitative risk analysis
      3. Perform quantitative risk analysis
      4. Plan risk response
   8. Plan procurement management
      1. Determine procurement strategy
      2. Craft procurement strategy table
      3. Review and finalise procurement strategy table
      4. Craft procurement management table
   9. Plan quality management
      1. Determine quality strategy
      2. Craft quality plan table
      3. Review and finalize quality plan table
   10. Website planning
       1. Identify website purpose
       2. Identify website requirements
       3. Craft website concept
       4. Review and finalize website concept
   11. Application
       1. Identify application purpose
       2. Identify application requirements
       3. Craft application concept
       4. Review and finalize application concept
   12. Server management
       1. Explore business systems
       2. Identify optimal business system
       3. Identify server management choices
       4. Craft sever management plan table
       5. Review and finalize server management plan table
3. **Executing** 
   1. Intranet website content
      1. Templates and tools
      2. AFL material
         1. Articles
         2. Links
      3. Contact players
      4. Merchandise
      5. Ticketing
   2. Intranet application content
      1. Templates and tools
      2. AFL material
         1. Articles
         2. Links
      3. Health care information material
      4. Accessibility features
      5. Social media campaign
   3. Intrant website design
   4. Intrant website construction
   5. Intrant website testing
   6. Intrant website promotion
   7. Intrant website roll-out
   8. Intrant application design
   9. Intrant application construction
   10. Intrant application testing
   11. Intrant application promotion
   12. Intrant application roll-out
   13. Project benefits measurement
4. **Monitoring and Controlling**
   1. Assumption table management
   2. Procurement management
   3. Server management
   4. Time management
   5. Stakeholder engagement management
   6. Progress reports
5. **Closing**
   1. Prepare final Gantt chart
   2. Prepare final scope table
   3. Prepare final project report
      1. Collect and review progress reports
         1. Create progress summary report
         2. Review and finalize progress summary report
      2. Review and finalize final project report
      3. Prepare glossary of terms
   4. Prepare final project presentation
      1. Title page
      2. Executive summary
      3. Table of contents
      4. Report summary