## Risk Analysis
Risk Management Plan
No | Rank (1-10) | Risk | Root causes | Triggers | Response | Probability | Impact | Consequence
R1 | 8 | Scope is incorrectly defined | Miscommunication |  | The deadline may need increasing, or the project's quality may suffer | 10% | High | Features are missed out, deadline may increase and stakeholders are dissatisfied
R2 | 5 | Scope creep occurs | Miscommunication |  | The deadline may need increasing, or the project's quality may suffer | 90% | Medium | Features are added that weren't initially catered for
R3 | 7 | Key stakeholders don't understand the scope | Miscommunication |  | Understand this early. May lead to lack of quality. Explain 100% to effected stakeholder(s) | 65% | High | Higher stakeholder expectations, leading to either scope creep or dissatisfaction
R4 | 10 | Risks are overlooked | Lack of planning |  | Ongoing risk management iterations. Unknown further response(s) | 15% | High | Unknown consequences can occur
R5 | 6 | Project timeline is misunderstood | Miscommunication |  | Ensure proper communication to effected person(s) | 5% | Medium | A loss in quality or a delayed project
R6 | 8 | Project dependencies are incorrect | Lack of planning |  | Correct issue, reorganise deadlines utilising slack/float | 5% | High | Delayed project and/or lost productivity
R7 | 9 | Requirements are incorrectly defined | Lack of planning |  | Reiterate requirements, clearly defining with client(s) and stakeholder(s) | 40% | High | Project comes to a halt
R8 | 8 | Stakeholders don't understand the requirements | Miscommunication |  | Clearly explain them based on stakeholder communication plan | 20% | High | They expect more (or less) than what is underway
R9 | 4 | Team members don't understand the requirements | Miscommunication |  | Clearly explain them, making sure that they are understood. Review previous work. | 10% | Medium | Poor quality, unguided work
R10 | 6 | Key stakeholders don’t like the project | Miscommunication, identified incorrect stakeholders |  | Identify other stakeholders | 12% | Medium | Project doesn't go ahead
R11 | 8 | Cost estimates are underestimated | Lack of planning |  | Seek funds/investors. Possibly sacrifice quality. | 75% | High | Lack of resources (money), may have to sacrifice quality
R12 | 1 | Cost estimates are overestimated | Lack of planning |  | Non-issue | 60% | Low | Loss of resources, could have increased productivity
R13 | 6 | Key stakeholders don't care about the project anymore | Expectation management |  | Revisit stakeholder management plan and communicate accordingly. | 15% | Medium | Project loses momentum as team members lose motivation
R14 | 10 | Lack of communication | Cultural issues, poor communication management |  | Enforce daily communication via standups so that everyone is on the same page. | 35% | High | Misunderstanding of many other parts. May lead to other risks appearing.
R15 | 8 | Lack of resources | Lack of planning |  | Restructure finances | 15% | High | Unable to complete the project
R16 | 9 | Lack of staff training | Hiring issue |  | Train existing staff or rehire | 5% | High | Unable to complete the project
R17 | 3 | Team member quits | Burnout |  | Offer position +10%. Otherwise, hire. | 75% | Low | Must find a new member. Deadline possibly increases
R18 | 7 | Suppliers drop out | Economic issues |  | Find other supplier based on feedback. | 15% | High | Must find a new supplier. Deadline possibly increases
R19 | 2 | Team member conflict | Human nature |  | Cycle a member out or separate working environments | 30% | Low | Creates conflict and may cause possible sabotage
R20 | 6 | Stakeholders argue over decisions | Miscommunication, human instinct |  | Restructure management plan | 15% | Medium | May lead to lack of interest