## Sheet1
Top 5 Risks
No | Risk | Response
R12 | Costs are incorrectly estimated | Re-establish cost estimates for the remainder for the project. Possible external invesmentors may be required.
R3 | Scope creep occurs | The deadline may need increasing, or the project's quality may suffer. Focus on minmalism, revisit out-of-scope documentation.
R23 | Schedule is unrealistic | Based on requirements, re-estimate schedule and do this multiple times in the project, include slack to account for overdue tasks
R1 | Requirements are impossible to achieve | Revisit and don't sign off on requirements until they have been approved by all internal stakeholders including project leads. | Scope must be re-evaluated, making sure that requirements are matched
R26 | Cannot gain approval from Department of Corrective Services | Revise contract and proposed deal for the Dept. of Corrective Services. Consult with Strategy & Operations for alternatives. | The deadline may need increasing, or the project's quality may suffer
Reiterate requirements, clearly defining with client(s) and stakeholder(s)
Clearly explain them based on stakeholder communication plan
Clearly explain them, making sure that they are understood. Review previous work.
Identify other stakeholders
Seek funds/investors. Possibly sacrifice quality.
Revisit stakeholder management plan and communicate accordingly.
Enforce daily communication via standups so that everyone is on the same page.
Restructure finances
Train existing staff or rehire
Offer position +10%. Otherwise, hire.
Find other supplier based on feedback.
Cycle a member out or separate working environments
Restructure management plan