## Risk Register
Risk Register
NB: Frodo, Sam, Pippin and Bilbo are the project management team
No | Risk | Root cause | Owner | Probability | Impact | Consequence
R1 | Requirements are impossible to achieve | Unreal expectations | Pippin | 40% | High | Requirements must be reevaluated and the projecct can't go ahead as it is currently defined
R2 | Scope doesn't meet requirements | Miscommunication | Frodo | 10% | High | Features are missed out, deadline may increase and stakeholders are dissatisfied
R3 | Scope creep occurs | Miscommunication | Sam | 90% | Medium | Features are added that weren't initially catered for
R4 | Key stakeholders don't understand the scope | Miscommunication | Frodo | 65% | High | Higher stakeholder expectations, leading to either scope creep or dissatisfaction
R5 | Risks are overlooked | Lack of planning | Bilbo | 15% | High | Unknown consequences can occur
R6 | Project timeline is misunderstood | Miscommunication | Bilbo | 5% | Medium | A loss in quality or a delayed project
R7 | Project dependencies are incorrect | Lack of planning | Sam | 5% | High | Delayed project and/or lost productivity
R8 | Requirements are incorrectly defined | Lack of planning | Frodo | 40% | High | Project comes to a halt
R9 | Stakeholders don't understand the requirements | Miscommunication | Pippin | 20% | High | They expect more (or less) than what is underway
R10 | Team members don't understand the requirements | Miscommunication | Frodo | 10% | Medium | Poor quality, unguided work
R11 | Key stakeholders don’t like the project | Miscommunication, identified incorrect stakeholders | Frodo | 12% | Medium | Project doesn't go ahead
R12 | Costs are incorrectly estimated | Lack of planning | Pippin | 75% | High | Lack of resources (money), may have to sacrifice quality
R13 | Key stakeholders don't care about the project anymore | Expectation management | Bilbo | 15% | Medium | Project loses momentum as team members lose motivation
R14 | Lack of communication | Cultural issues, poor communication management | Sam | 35% | High | Misunderstanding of many other parts. May lead to other risks appearing
R15 | Lack of resources | Lack of planning | Sam | 15% | High | Unable to complete the project
R16 | Lack of staff training | Hiring issue | Pippin | 5% | High | Unable to complete the project
R17 | Team member quits | Burnout | Frodo | 75% | Low | Must find a new member. Deadline possibly increases
R18 | Suppliers drop out | Economic issues | Bilbo | 15% | High | Must find a new supplier. Deadline possibly increases
R19 | Team member conflict | Human nature | Pippin | 30% | Low | Creates conflict and may cause possible sabotage
R20 | Stakeholders argue over decisions | Miscommunication, human instinct | Pippin | 15% | Medium | May lead to lack of interest
R21 | Inexperienced project managers | Hiring issue | CEO | 40% | High | Negligence in regard to the entire project. Failure to complete
R22 | Cultural insensitive project managers | Experience issue | Hiring Manager | 15% | High | Negligence in regard to the major stakeholders of the project. Making the project less effective, significantly delaying the completion time
R23 | Schedule is unrealistic | Inexperienced project managers | Hiring Manager | 60% | High | Schedule must be reevaluated, possibly prolonging the project, increasing costs and need for resources
R24 | Stakeholders can't agree on the project | Improper understanding of requirements | Pippin | 35% | Medium | Stakeholder friction may occur, causing a major stakeholder to depart the project. Possible miscommunication in regards to requirements
R25 | Cannot gain approval for a home football ground | Stadiums not wanting to double up on home-teams | Outreach | 3% | High | No stadium to call home. Possibly share a home stadium with a local team.
R26 | Cannot gain approval from Department of Corrective Services | Unable to see the benefits of the programme | Outreach | 55% | High | Major hit to recruitment. Revisit contract to the department
R27 | Cannot gain approval from indigenous elders for players | Incorrect communication protocols | Recruitment | 20% | Medium | Minor hit to recruitment. Revisit at a later date, researching protocols
R28 | Hardware provided underperforms, not meeting requirements | Supplier incompetence | Supplier | 15% | High | Increase in costs and schedule, unless covered by guarantee
R29 | Supplier is late on delivery | Supplier incompetence | Supplier | 15% | Medium | Increase in schedule, possible cost increase
R30 | Supplier doesn’t enforce guarantees | Poor supplier contract | Supplier | 10% | Medium | Increase costs for legal-action or new infrastructure
R31 | Supplier doesn't enforce product warranties | Poor supplier contract | Supplier | 10% | Medium | Increase costs for products
R32 | Incorrect insurance cost estimates | Use of incorrect pricing sheets | CFO | 7% | Medium | Increased costs and debt to cover the rest when insurance is required
R33 | Some project items aren't fully insured | Inappropriate level of cover | CFO | 2% | High | Partial payback if insurance is required. Increased costs and debt to cover the rest
R34 | Negligence isn't covered in insurance | Inappropriate terms in insurance contract | CFO | 2% | High | Increased costs when negligence occurs to assets. Possible debt.
R35 | Supplier completes order incorrectly | Supplier incompetence | Supplier | 23% | Low | Increased schedule due to waiting on proper shipment
R36 | Supplier cannot complete order on time | Supplier incompetence | Supplier | 17% | Medium | Increased schedule due to waiting on proper shipment
R37 | Supplier cannot complete order | Supplier incompetence | Supplier | 10% | High | Increased schedule due to finding a contingency supplier
R38 | Social media followers slander players or the team | Societal causes | Social media moderator | 60% | Medium | Lowers club reputation, increased costs to moderate social media
R39 | Unacceptable content is shared online via The Mudcrabs accounts | Lack of moderation on social media manager | Social media moderator | 5% | High | Lowers club reputation, increased costs to moderate social media
R40 | Prisoner escapes during training session | Willingness to be free | Dept of Corrective Services | 3% | High | Lack of team member, possible fines, poor club reputation
R41 | Prisoner escapes during transport | Willingness to be free | Dept of Corrective Services | 3% | High | Lack of team member, possible fines, poor club reputation
R42 | Prisoner escapes during football game | Willingness to be free | Dept of Corrective Services | 8% | High | Lack of team member, possible fines, poor club reputation
R43 | Team members start gambling heavily | Addiction | Dept of Racing, Gaming and Liquor | 5% | High | Team member possibly unfit for game due to addiction
R44 | Racism occurs against The Mudcrabs | Societal causes | PR Officer | 60% | Low | May instigate a larger conflict against races, possible legal costs
R45 | Racism occurs on behalf of The Mudcrabs | Pushback / societal causes | PR Officer | 12% | High | Decreases club reputation, possible legal costs
R46 | A physical fight occurs during training | High stress environment | Coaching staff | 7% | Low | Decrease overall club reputation and morale. Possible legal costs, lack of team members.
R47 | A physical fight occurs during an official match | Unsportsman-like conduct | Coaching staff | 17% | High | Decrease overall club reputation and morale. Possible legal costs, lack of team members.
R48 | Team members abuse drugs | Addiction | Health Department | 8% | High | Team member possibly unfit for game due to addiction and health
R49 | Team member gets injured during training | Inadequate staff training leading warmups | Medical staff | 10% | Medium | Missing team member for following game/s
R50 | Team member gets injured during an official match | High performance and high impact contact | Medical staff | 40% | Medium | Missing team member for following game/s
R51 | Team member is unavailable due to walkabout | Cultural responsibility | Outreach | 85% | Medium | Missing team member for following games
R52 | Hardware needs are understated to suppliers | Miscommunication of requirements | Pippin | 50% | High | Increased costs with correcting the issue. ICT infrastructure may be unusable, increasing timeline.
R53 | Hardware needs are overstated to suppliers | Miscommunication of requirements | Pippin | 50% | Low | Increased costs with overspending
R54 | Improper hardware procurement | Underlying ethical issues | Bilbo | 10% | Medium | Decrease club reputation and possibly didn't find the best price, therefore increasing costs
R55 | Overlook potential suppliers | Bias based on previous projects | Pippin | 3% | High | Possibly not finding the best price; increasing costs.
R56 | Products are damaged in transport from supplier | Shipping and handling negligence | Supplier | 7.5% | Medium | Increased schedule due to waiting on proper shipment
R57 | Favouritism when choosing suppliers | Bias based on previous projects | Bilbo | 3% | High | Possibly not finding the best price; increasing costs. Products may be incompatible.
R58 | Users needs are completely overlooked | Poor requirements | Sam | 2% | High | Missing the largest stakeholder undermines the business, resulting in less memberships
R59 | Budget cuts occur during the project | Improper cost estimates | CFO | 12% | High | Decrease in project work quality, possible lay offs.
R60 | Employees work slower than previously estimated | Previously unobserved employees | Frodo | 45% | High | Increased schedule and costs, possible new hires
R61 | Hired too little people | Inexperienced hiring manager | Hiring Manager | 70% | Medium | Increased schedule, costs associated with new hires
R62 | Hired too many people | Inexperienced hiring manager | Hiring Manager | 25% | Low | Increased costs with overspending, members lose their jobs
R63 | A task takes longer than expected | Poor task management | Sam | 100% | Medium | Increased schedule
R64 | Social media accounts are compromised | Social engineering attack | Security team | 4% | High | Possible defamation, reduction of club value and reputation
R65 | Slow adoption rate of smartphone application | Lack of advertisment | PR Officer | 23% | High | Slow build up of membership and slow spread of news. Increased costs for media broadcasting and communication.
R66 | Security vulnerabilities eventuate on website | Outdated software | Security team | 65% | High | Possible defamation, reduction of club value and reputation
R67 | Security vulnerabilities eventuate in smartphone applications | Outdated software | Security team | 65% | High | Possible defamation, reduction of club value and reputation
R68 | High data use from smartphone applications | Poor software engineering | App Developers | 5% | High | Increased data costs for low-income stakeholders, causing a lack of use in the app
R69 | Website servers crash | Denial of service attack | CIO | 1% | High | Increased costs due to fixing servers, lower reputation, possible malicious intent
R70 | Smartphone apps crash | Inadequate servers | CIO | 1% | High | Increased costs due to fixing servers, lower reputation, possible malicious intent