## Risk Analysis
Risk Management Plan
Risk | Consequence | Probability | Response
Scope is incorrectly defined | Features are missed out, deadline may increase and stakeholders are dissatisfied | 10% | The deadline may need increasing, or the project's quality may suffer
Scope creep occurs | Features are added that weren't initially catered for | 90% | The deadline may need increasing, or the project's quality may suffer
Stakeholders don't understand the scope | Higher stakeholder expectations, leading to either scope creep or dissatisfaction | 65% | Understand this early. May lead to lack of quality. Explain 100% to effected stakeholder(s)
Risks are overlooked | Unknown consequences can occur | 15% | Ongoing risk management iterations. Unknown further response(s)
Project timeline is misunderstood | A loss in quality or a delayed project | 5% | Ensure proper communication to effected person(s)
Project dependencies are incorrect | Delayed project and/or lost productivity | 5% | Correct issue, reorganise deadlines utilising slack/float
Requirements are incorrectly defined |  | 40% | Reiterate requirements, clearly defining with client(s) and stakeholder(s)
Stakeholders don't understand the requirements | They expect more (or less) than what is underway | 20% | Clearly explain them based on stakeholder communication plan
Team members don't understand the requirements | Poor quality, unguided work | 10% | Clearly explain them, making sure that they are understood. Review previous work.
Key stakeholders don’t like the project | Project doesn't go ahead | 12% | -
Cost estimates are underestimated | Lack of resources (money), may have to sacrifice quality | 75% | Seek funds/investors. Possibly sacrifice quality.
Cost estimates are overestimated | Loss of resources, could have increased productivity | 60% | -
Key stakeholders don't care about the project anymore | Project loses momentum as team members lose motivation | 15% | Revisit stakeholder management plan and communicate accordingly.
Lack of communication | Misunderstanding of many other parts. May lead to other risks appearing. | 35% | Enforce daily communication via standups so that everyone is on the same page.
Lack of resources | Unable to complete the project | 15% | -
Lack of staff training | Unable to complete the project | 5% | Get training?
Team member quits | Must find a new member. Deadline possibly increases | 75% | Offer position +10%. Otherwise, hire.
Suppliers drop out | Must find a new supplier. Deadline possibly increases | 15% | Find other supplier based on feedback.
Team members argue | Creates conflict and may cause possible sabotage | 30% | Cycle a member out or separate working environments
Stakeholders argue over decisions, causing conflict | May lead to lack of interest | 15% | -

## Notes
Magnitude of the Consequence
Insignificant - Easily handled within the normal course of operations with no additional costs. (Impact level <10.)
Minor - Some disruption within the normal functions. Manageable risk with minimum estimated cost. (Impact level between 11 and 25.)
Moderate - Immediate time/resource reallocation will be necessary with a moderate estimated cost. (Impact level between 26 and 50.)
Major - Operations are severely disrupted and significant risk of failure to part of the business is possible. (Impact level between 51 and 75.)
Critical - Significant going concerns exists with the business and the risk is classified as critical. (Impact level >75.)
Probability of the Consequence
Remote - Probability of less than 10%.
Highly Unlikely - Probability between 10% and 35%.
Possible - Probability between 36% to 50%.
Probable - Probability between 51% to 60%.
Highly Likely - Probability 61% to 90%.
Certain - Probability above 90%.